## Implementation Plan
Phase | Goal | Backend Tasks | Frontend Tasks | Infra / Data Tasks | Key Outputs | Exit Criteria
Phase 0 | Freeze target architecture and contracts before code movement | Define service boundaries; define job state machine; define artifact versioning; define normalized report schema; define decision thresholds | Confirm UX for create-job, processing states, result views | Choose Firestore vs Cloud SQL; choose Pub/Sub vs Cloud Tasks; choose first detector set | Architecture doc; API contract doc; job-state diagram; report JSON schema | No ambiguity remains about orchestration, generation, validation, fix loop, or final report ownership
Phase 1 | Add async job foundation without splitting services yet | Add job model and status endpoints; store artifact versions; wrap current synchronous generate flow in background execution | Update processing page to poll job status; show real stage progress; handle refresh/re-entry with job_id | Provision job store; create storage layout for draft_v1/v2/v3 and reports | Async workflow shell; job polling; resumable processing UI | User can upload, start a job, refresh the page, and still see current progress and final result
Phase 2 | Extract generation into a dedicated generation-service | Move structuring, writing, citation, and formatting into generation-service; stop default pipeline after IEEE formatting; persist formatted draft artifact | Point processing flow to orchestrator-driven generation status instead of direct long-running generate call | Deploy generation-service on Cloud Run; connect artifact storage for formatted drafts | Generation-service; formatted draft output; generation metadata contract | Orchestrator can request generation and receive a formatted draft artifact without humanizer or originality blocking
Phase 3 | Build fast validation service and remove external providers from baseline flow | Implement chunking; lexical overlap checks; citation-aware overlap logic; stylometry; perplexity; basic AI-risk scoring; aggregator v1 | Show fast-validation stage and early-exit result states in UI | Deploy validation-service; create score/result collections; store section-level flags | Fast validation-service; aggregator v1; internal baseline validation | Most jobs complete through fast validation only, with no Winston or Copyleaks dependency
Phase 4 | Extract fix loop into a dedicated fix-service | Move humanizer logic out of default generation path; implement flagged-section rewrite only; add before/after tracking; add loop-safe revalidation hooks | Add diff / before-after views for revised sections; expose fix-loop state in processing and report UI | Deploy fix-service; store immutable revised drafts and change logs | Fix-service; draft version chain; controlled rewrite loop | Orchestrator can send flagged sections for revision and receive draft_v2/v3 plus change metadata
Phase 5 | Add deep validation layer for borderline cases | Integrate RADAR first; add Open-Detector second; add OUTFOX later; add semantic plagiarism checks; calibrate fusion model | Show deep-validation status and confidence bands in reports | Provision GPU runtime if needed; configure model-serving and batch strategy | Deep validation-service; calibrated ensemble; borderline escalation path | Borderline jobs can be escalated to high-accuracy validation without running GPU models on every job
Phase 6 | Build final reporting and dashboard experience | Produce final AI score, plagiarism/originality score, heatmaps, highlighted spans, audit trail, and job timeline APIs | Make plagiarism/results page live; add report drill-down, section heatmap, and before/after comparison | Persist final reports and analytics-friendly summaries | Real dashboard; final report APIs; audit history | Users can inspect the full workflow outcome from upload to accepted draft and report
Phase 7 | Production hardening and scale readiness | Add idempotency handling; dead-letter strategy; replay safety; structured tracing; timeouts; fallback paths; cost caps | Improve user-facing error states, retry UX, and support visibility | Add monitoring, alerting, stage latency metrics, failure dashboards, and cost tracking | Operational hardening; observability; cost controls | System can survive retries, failures, traffic spikes, and partial service outages without corrupting jobs

## Work Items
Track | Priority | Phase | Work Item | Owner Area | Dependencies | Definition of Done
Track A | P0 | Phase 0 | Define job state machine and legal transitions | Backend / Architecture | None | State diagram and state enum approved
Track A | P0 | Phase 0 | Define event payloads for generate, validate, fix, finalize | Backend / Architecture | Job model | Versioned event contracts documented
Track A | P0 | Phase 1 | Create job table/collection and artifact version model | Backend | State machine | Job records persist status, stage, iteration, and artifact URIs
Track A | P0 | Phase 1 | Add orchestrator endpoints: create job, get status, get result | Backend | Job store | Endpoints return stable IDs and current state
Track B | P0 | Phase 1 | Update processing page to poll by job_id instead of waiting on one request | Frontend | Orchestrator status endpoint | Processing page survives refresh and resumes progress
Track B | P1 | Phase 1 | Show real stage labels: queued, generating, validating, fixing, done, failed | Frontend | Job state API | Users see backend-driven progress
Track C | P0 | Phase 2 | Split generation path to stop after formatting and write formatted draft artifact | Backend / Generation | Phase 1 async shell | Formatted draft available without humanizer/originality pass
Track C | P1 | Phase 2 | Move current internal pipeline behind generation-service API | Backend / Generation | Formatted draft artifact contract | Generation-service can run independently
Track D | P0 | Phase 3 | Implement chunking and section-aware overlap analysis | Backend / Validation | Generation artifact schema | Validation can score by section/window
Track D | P0 | Phase 3 | Implement stylometry and perplexity features | Backend / Validation | Chunking | Feature outputs stored for aggregator
Track D | P0 | Phase 3 | Build aggregator v1 with clean / borderline / flagged routing | Backend / Validation | Feature outputs | Deterministic routing works on baseline jobs
Track E | P1 | Phase 4 | Extract current humanizer into fix-service with flagged-section-only rewrites | Backend / Fix | Validation flags | Fix-service returns updated draft version and change log
Track E | P1 | Phase 4 | Add revalidation of changed sections only | Backend / Fix | Fix-service output | Revalidation avoids full document recompute when possible
Track F | P2 | Phase 5 | Integrate RADAR as first deep-validation model | Backend / ML | Fast validation stable | Borderline jobs can call RADAR and store results
Track F | P2 | Phase 5 | Integrate Open-Detector and add calibration dataset workflow | Backend / ML | RADAR integration | Ensemble scores can be calibrated on academic text set
Track G | P1 | Phase 6 | Build live results page with AI score, overlap score, heatmap, and revisions | Frontend | Report APIs | Report page is fully data-driven
Track H | P0 | Phase 7 | Add idempotency keys and replay-safe processing | Backend / Platform | All prior phases | Duplicate submits do not create corrupted or duplicate jobs
Track H | P1 | Phase 7 | Add monitoring, tracing, alerting, and cost dashboards | Platform / Infra | Production services deployed | Operators can debug stage latency, failures, and spend

## Milestones
Milestone | Includes | Why It Matters
M1 - Async Foundation | Phase 0 + Phase 1 | Removes the blocking generate request and creates the backbone for every later service split
M2 - Generation Extraction | Phase 2 | Preserves your current content quality while isolating generation from validation and fix logic
M3 - Provider Removal | Phase 3 | Lets you stop depending on third-party baseline validation and own the scoring path
M4 - Controlled Revision Loop | Phase 4 | Turns the humanizer into a bounded repair service instead of a default generation stage
M5 - High-Accuracy Escalation | Phase 5 | Adds expensive deep models only where they improve borderline decisions
M6 - User-Facing Productization | Phase 6 + Phase 7 | Makes the system inspectable, supportable, and production-ready